## Budget vs Actual
Budget vs Committed vs Actual Tracker - CivilPilot: Budget vs Actual
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project
Budget version
Approved by
Approved on
Report as of
Cost code | Description | Budget | Committed (open) | Actual | Budget left | % used | % spent
CC-01 | Earthwork and foundation | 1800000 | 30000 | 1710000
CC-02 | RCC frame | 6200000 | 1730000 | 4120000
CC-03 | Masonry and plaster | 3800000 | 1677500 | 1968500
CC-04 | Site labour | 1200000 | 0 | 930000
CC-05 | Finishes | 2600000 | 2380000 | 460000
Total
Shaded rows are samples: delete or overwrite them.
• Sample rows are illustrative figures only.
• Committed (open) = approved orders not yet billed. Take it from the 'Balance to bill' total per cost code on the Commitments sheet.
• Actual = cost billed, received or paid: supplier bills, certified RA bills, wages and site expenses.
• Budget left = Budget - Committed - Actual. A negative value means orders already placed exceed the budget.
• Format % used and % spent as percentages.

## Commitments
Budget vs Committed vs Actual Tracker - CivilPilot: Commitments
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project
Cost code | Type (PO / WO) | Reference no. | Vendor / subcontractor | Date | Order value | Billed to date | Balance to bill
CC-02 | PO | PO-031 | Sample Steel Traders | 2026-08-04 | 2600000 | 1450000
CC-03 | WO | WO-014 | Sample Masonry Works | 2026-06-20 | 3646000 | 1968500
CC-05 | PO | PO-044 | Sample Tile Suppliers | 2026-09-12 | 1850000 | 460000
Total
Shaded rows are samples: delete or overwrite them.
• One row per approved purchase order or work order. Sample rows are illustrative.
• Update 'Billed to date' when each supplier bill or RA bill is certified.
• To total balance by cost code, use =SUMIF(A:A,"CC-03",H:H) or a pivot table.