## DPR
Daily Progress Report (DPR): DPR
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project
Location / work front
Date
Shift
Weather
Prepared by
Approved by
Activity | Location | Quantity | Unit | Labour (nos) | Contractor | Material used | Remarks / hindrance
3rd floor slab shuttering | Tower A | 99 | sqm | 14 | Sample Contractor 1 | Plywood, props | Props checked by engineer
3rd floor column concreting | Tower A | 15 | cum | 11 | Sample Contractor 2 | M25 ready-mix | Cube samples taken
1st floor block masonry | Tower B | 64 | sqm | 9 | Sample Contractor 1 | AAC blocks, mortar
Ground floor conduit laying | Tower B | 141 | rmt | 4 | Sample Contractor 3 | PVC conduit | Waiting for junction boxes
Total
Shaded rows are samples: delete or overwrite them.
• Fill one sheet per site per day. Record quantities with units, not 'in progress'.
• Attach photos for each activity and keep them with this report.
• Note anything that stopped or slowed work in the Remarks column.
• Sample rows are examples only: delete them before use.

## Material & equipment
Daily Progress Report (DPR): Material & equipment
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project
Date
Material / equipment | Unit | Received today | Used today | Short / needed tomorrow | Remarks
Cement OPC 53 | bag | 200 | 140
TMT 12 mm | MT | 0 | 1.2 | 2 MT for column work
Concrete mixer | hours |  | 6 |  | Hired
Shaded rows are samples: delete or overwrite them.
• Plan tomorrow's material here so the office can arrange it in time.