## Stock check
Material Reconciliation Format (Construction): Stock check
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Company
Project / site
Period from
Period to
Prepared by (store keeper)
Checked by
Material code | Material | Unit | Opening stock | Received | Issued | Book closing | Physical stock | Stock difference | Remarks
CEM-01 | SAMPLE - Cement (OPC) | bag | 150 | 1200 | 1180 |  | 166 |  | Sample row - delete
STL-12 | SAMPLE - TMT steel 12 mm | kg | 4200 | 18000 | 16950 |  | 5250 |  | Sample row - delete
SND-01 | SAMPLE - M-sand | cum | 40 | 180 | 170 |  | 48 |  | Sample row - delete
Shaded rows are samples: delete or overwrite them.
• One row per material. Use one unit per material throughout (bags or tonnes, kg or MT - never mixed).
• Opening stock = last period's PHYSICAL closing stock.
• Received = total of goods receipts in the period; Issued = total issued from store to the work.
• Book closing = Opening + Received - Issued. Stock difference = Physical - Book closing; a negative figure means material is missing from the store.
• No column totals: materials are in different units.

## Theoretical working
Material Reconciliation Format (Construction): Theoretical working
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project / site
Period
Activity | Material | Work done (measured) | Work unit | Consumption per unit of work (from your estimate) | Material unit | Theoretical quantity
SAMPLE - RCC, columns and slab | Cement (OPC) | 120 | cum | 8 | bag
SAMPLE - Internal plastering | Cement (OPC) | 1500 | sqm | 0.13 | bag
SAMPLE - Steel for work done, per bar bending schedule | TMT steel 12 mm | 16400 | kg | 1 | kg
Shaded rows are samples: delete or overwrite them.
• Take work done from measured records (DPR or measurement book), not from estimated progress.
• Consumption per unit of work must come from YOUR estimate, rate analysis, mix design or bar bending schedule. The sample figures are assumptions for illustration, not norms.
• Add up the theoretical quantity for each material and carry it to the Consumption check sheet.

## Consumption check
Material Reconciliation Format (Construction): Consumption check
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project / site
Period from
Period to
Checked by (PM / QS)
Material code | Material | Unit | Theoretical consumption | Issued to work | Returned to store | Unused at work front | Actual consumption | Variance | Variance % | Allowed variance % (from contract / estimator) | Status | Reason for variance
CEM-01 | SAMPLE - Cement (OPC) | bag | 1155 | 1180 | 0 | 0 | [5 empty] | Sample row - delete
STL-12 | SAMPLE - TMT steel 12 mm | kg | 16400 | 16950 | 0 | 0 | [5 empty] | Sample row - delete
SND-01 | SAMPLE - M-sand | cum | 165 | 170 | 0 | 3 | [5 empty] | Sample row - delete
Shaded rows are samples: delete or overwrite them.
• Actual consumption = Issued to work - Returned to store - Unused at work front.
• Variance = Actual - Theoretical. Variance % = Variance / Theoretical x 100.
• Allowed variance % varies by contract, specification and type of work. Enter the figure from your contract or estimator; this template does not supply norms.
• Investigate any variance above the allowance, and any negative variance (often over-measured work or unrecorded issues).