## Material request
Material Request Form (Construction Site): Material request
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Company
Project / site
Request no.
Request date
Location / floor / block
Required by date
Priority (Low / Medium / High / Urgent)
Requested by (site engineer)
Approved by (project manager)
Sl. no. | Material code | Description (grade / size / brand) | Unit | BOQ item / cost code | Purpose / activity | Stock at site now | Requested qty | Approved qty | Estimated rate | Estimated value | Remarks
1 | CEM-01 | SAMPLE - Cement OPC 53 grade | bag | SAMPLE - RCC slab, 3rd floor | Slab pour | 40 | 320 |  | 380 |  | Sample row - rates are placeholders
2 | STL-10 | SAMPLE - TMT steel Fe 500D, 10 mm | kg | SAMPLE - RCC slab, 3rd floor | Slab reinforcement | 600 | 2400 |  | 62 |  | Sample row - delete
3 | BRK-01 | SAMPLE - Red clay bricks, standard size | nos | SAMPLE - Brickwork 230 mm | 2nd floor walls | 1500 | 12000 |  | 9 |  | Sample row - delete
Total
Shaded rows are samples: delete or overwrite them.
• Raise one request per need, with a required-by date that leaves time to order and deliver.
• Describe the material fully (grade, size, brand if specified) so purchase can order without calling the site.
• Fill Stock at site now before requesting, so the office can see why more is needed.
• Approved qty is filled by the approver. Estimated value uses Approved qty when it is filled, otherwise Requested qty.
• Sample rates are placeholders for illustration, not market rates.

## Request register
Material Request Form (Construction Site): Request register
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Project / site
Month
Request no. | Request date | Requested by | Material | Unit | Requested qty | Required by | Priority | Status (Pending / Approved / Rejected / Fulfilled / Cancelled) | PO no. | GRN no. | Date received | Days late | Remarks
MR-0031 | SAMPLE | SAMPLE - Site engineer | SAMPLE - Cement OPC 53 grade | bag | 320 |  | High | Fulfilled | PO-0009 | GRN-0014 |  |  | Sample row - enter dates as real dates
MR-0032 | SAMPLE | SAMPLE - Site engineer | SAMPLE - TMT steel Fe 500D, 10 mm | kg | 2400 |  | Medium | Approved | PO-0011 |  |  |  | Sample row - delete
Shaded rows are samples: delete or overwrite them.
• One row per material per request. Update the status as the request moves from site to office to supplier.
• Link each request to its PO and GRN so you can trace every delivery back to the site's need.
• Days late = Date received - Required by. Enter both as dates; a request with no required-by date cannot be tracked.