## Work Order
Work Order Format for Civil Work - CivilPilot: Work Order
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Company
Project
Work order no.
Work order date
Subcontractor
Subcontractor GSTIN
Subcontractor PAN
Scope of work
Exclusions / material by company
Start date
Completion date
Measurement method
Billing cycle
Retention % and release terms
Advance and recovery terms
Variations
Item no. | Description | Cost code | Unit | Quantity | Rate | Amount | Remarks
1 | Brickwork 230 mm in CM 1:6 | CC-03 | cum | 300 | 6500 |  | Sample figures
2 | Internal plaster 12 mm in CM 1:4 | CC-03 | sqm | 4000 | 320 |  | Sample figures
3 | PCC 1:4:8 below flooring | CC-03 | cum | 80 | 5200 |  | Sample figures
Total
Shaded rows are samples: delete or overwrite them.
• Sample rows are illustrative figures, not market rates.
• Use the same item descriptions and cost codes as your BOQ.
• Write scope inclusions and exclusions clearly, including who supplies material, tools and water.
• Changes to items or quantities need a written, approved variation before they are billed.
• Both parties sign and date the work order. General information only; have larger work orders reviewed by your advisor.

## Progress
Work Order Format for Civil Work - CivilPilot: Progress
Free template from CivilPilot · civilpilot.com · Construction site management software for India
Work order no.
Progress as of
Item no. | Description | Unit | Ordered qty | Rate | Done to date | Balance qty | % complete | Value done | Value balance
1 | Brickwork 230 mm in CM 1:6 | cum | 300 | 6500 | 165
2 | Internal plaster 12 mm in CM 1:4 | sqm | 4000 | 320 | 1500
3 | PCC 1:4:8 below flooring | cum | 80 | 5200 | 80
Total
Shaded rows are samples: delete or overwrite them.
• Format the % complete column as a percentage.
• Take 'Done to date' from measured quantities and daily progress reports.
• This sheet feeds the cumulative quantity column of your RA bill.